## Slide 1: 1. Automation Planning & Setup (Weeks 1–2)
Objective: Enhance the existing Selenium + Java framework by integrating AI-driven capabilities (Copilot, Locator Healing, and Reusability Enhancements) to strengthen automation scalability and maintainability.
Activities:
Conduct kick-off meeting to define enhancement scope, AI adoption plan, and success metrics.
Review existing framework components and identify improvement areas for reusability and self-healing.
Integrate Copilot-assisted code generation for faster utility updates.
Enhance framework with AI-based locator healing and dynamic element handling.
Refactor reusable utilities (login, navigation, validation) to align with new standards.
Configure CI/CD pipeline updates for automated validation and report tracking.

## Slide 2: 2. Sprint 1 & 2 – High Priority Automation (Weeks 3–6)
Objective: Automate critical high priority regression test cases with reusable components.
Activities:
Automate 150 high priority test cases with average 6 Hrs effort per case.
Integrate Copilot for assisted coding to reduce manual effort by 25–30%.
Conduct daily standups to discuss blockers and progress.
Perform code reviews and validations with manual QA team.
Execute scripts via CI/CD and track results in Allure/Extent Reports.

## Slide 3: Planned High Priority KPIs & Sub-KPIs – Sprint 1 & 2 (Weeks 3–6)
Goal: Plan and automate 150 high-priority regression test cases within this sprint to establish a strong reusable automation foundation
KPI | Target | How We’ll Achieve
% of Test Cases Automated | 100 % (150 TCs) | Weekly backlog + daily stand-ups + Jira tracking
Avg. Automation Time | ≤ 6 hrs per TC | Reusable components + Copilot support
CI/CD Execution Success | ≥ 95 % Pass Rate | Early integration + pipeline validation
QA Validation Coverage | 100 % reviewed by manual QA | Parallel execution and sign-off

## Slide 4: AI Assistance Efficiency (Copilot Impact)
Goal: Reduce manual effort by 25–30 %.
Sub-KPI | Target % | Achievement
Copilot-generated code snippets | 30 % target → achieved 28 % | Used Copilot for boilerplate and XPath utilities
Manual rework reduction | Target 20 % → achieved 22 % | Peer review + auto linting
Time saved per test case | Target 1.5 hrs saved → achieved 1.6 hrs | Reduced debug time via AI hints

## Slide 5: Collaboration & Delivery Cadence
Goal: Maintain team alignment and timely delivery.
Sub-KPI | Target % | Achievement
Daily stand-up attendance | 100 % → achieved 98 % | Used Teams & Jira updates
Blocker resolution within 24 hrs | 90 % → achieved 92 % | Assigned dedicated review owner
Sprint burn-down completion | ≥ 90 % → achieved 94 % | Bi-weekly progress review calls

## Slide 6: 3. Sprint 3 & 4 – Medium Priority Automation (Weeks 7–10)
Objective: Focus on core functional flows with stable automation coverage.
]Activities:
Automate 200 medium priority scenarios (average 5 Hrs per case).
Enhance reusable components for data driven and key word based testing.
Validate automated scripts through peer reviews and manual signoffs.
Execute automated suites in pipeline for continuous validation.
Optimize code for speed, maintainability, and error handling.

## Slide 7: 4. Sprint 5 – Low Priority & Regression Suite Stabilization (Weeks 11–12)
Objective: Automate remaining low priority and peripheral modules; stabilize the full regression suite.
Activities:
Automate 150 low priority test cases (average 2 hrs per case).
Combine all test cases into a unified regression suite.
Ensure scripts are compatible across all environments (QA/UAT).
Run nightly builds to check stability of test execution.
Monitor reports and track any flaky test cases.

## Slide 8: 5. CI/CD Integration, Review & Final Handover (Weeks 13–14)
Objective: Integrate final automation suite into CI/CD pipelines and conduct reviews before handover.
Activities:
Set up Jenkins or GitHub Actions for scheduled automation runs.
Validate execution and reporting accuracy through dashboards.
Conduct final sprint review, rework any failed test cases.
Prepare final automation summary and KT document for maintenance team.
Organize handover and signoff meeting with stakeholders.

## Slide 9: Summary – 3Month Automation Roadmap (ATK Project)
Objective: Deliver end to end automation suite within 3 months using BDD framework and reusable assets.
Activities:
Total Test Cases: 500 (High: 150, Medium: 200, Low: 150)
Team: 4 Members (2 Fulltime, 2 Parttime)
Framework: Selenium + Java + CI/CD + Copilot
Duration: 14 Weeks (~3 Months)
Productivity Gain: ~35% with AI Copilot and Reusability